## KPI Data
Week | Requests | Handling Min | FCR | Escalation | Class Accuracy | Hallucination | CSAT | Acceptance | Cost/Resolution | Metric definition | Formula
2026-08-17 | 2100 | 10.2 | 69% | 29% | 88% | 3.5% | 4.18 | 42% | 6.65 | Handling Min | Agent active minutes / resolved cases
2026-08-24 | 2250 | 9.4 | 71% | 27% | 91% | 2.4% | 4.22 | 49% | 6.2 | FCR | Resolved without reopen or follow-up / resolved
2026-08-31 | 2380 | 8.8 | 73% | 25% | 93% | 1.8% | 4.25 | 56% | 5.91 | Escalation | Escalated / analyzed
2026-09-07 | 2470 | 8.3 | 75% | 23% | 94% | 1.2% | 4.31 | 61% | 5.63 | Class Accuracy | Correct primary category / labeled sample
[10 empty] | Hallucination | Drafts with unsupported claim / reviewed drafts
[10 empty] | CSAT | Average post-contact score (1–5)
[10 empty] | Acceptance | Approved without edit / reviewed AI drafts
[10 empty] | Cost/Resolution | Attributed labor and AI cost / resolved cases
[10 empty] | Note | All values are illustrative portfolio data

## Dashboard
AI Support Pilot Dashboard
Illustrative four-week pilot data. Replace inputs on KPI Data to refresh formulas and charts.
Metric | Current |  | Metric | Current | Week | Handling Min
Average handling time | 9.175 |  | First contact resolution | 72% | 2026-08-17 | 10.2
Classification accuracy | 91.5% |  | Escalation rate | 26% | 2026-08-24 | 9.4
Hallucination rate | 2.225% |  | Response acceptance | 52% | 2026-08-31 | 8.8
Customer satisfaction | 4.24 |  | Cost per resolution | 6.0975 | 2026-09-07 | 8.3
Metric | Baseline | Target | Current | Status
Handling time (min) | 12 | 8.5 | 9.175 | Below
Classification accuracy | 84% | 90% | 91.5% | Met
Hallucination rate | 6% | 2% | 2.225% | Below
Customer satisfaction | 4.2 | 4.2 | 4.24 | Met
First contact resolution | 68% | 72% | 72% | Met | Week | Class Accuracy | Hallucination
Escalation rate | 22% | 30% | 26% | Within | 2026-08-17 | 0.88 | 0.035
Response acceptance | 0% | 55% | 52% | Below | 2026-08-24 | 0.91 | 0.024
Cost per resolution | 7.1 | 6.04 | 6.0975 | Below | 2026-08-31 | 0.93 | 0.018
[5 empty] | 2026-09-07 | 0.94 | 0.012

## Product Backlog
Jira Style Product Backlog
Prioritized pilot backlog with traceable requirement and story IDs.
Epic | Type | ID | Summary | Priority | Points | Sprint | Owner | Status | Trace
EPIC-1 | Story | US-001 | Automated classification and priority | Must | 8 | Sprint 1 | Product | Done | BR-02; FR-002–004
EPIC-1 | Story | US-002 | Approved knowledge retrieval and citations | Must | 13 | Sprint 1 | Engineering | Done | BR-03; FR-005–007
EPIC-2 | Story | US-003 | High-risk specialist routing | Must | 8 | Sprint 2 | Compliance | In UAT | BR-04; FR-009–010
EPIC-2 | Story | US-004 | Agent review and disposition actions | Must | 8 | Sprint 2 | Product | In UAT | BR-04; FR-011–012
EPIC-3 | Story | US-008 | Idempotent integration and correlation IDs | Must | 5 | Sprint 2 | Engineering | Done | FR-013–014; NFR-009
EPIC-3 | Task | TECH-01 | Prompt and model metadata audit event | Must | 5 | Sprint 2 | Engineering | In UAT | FR-008; NFR-008
EPIC-4 | Story | US-005 | Manager KPI dashboard and drill-through | Should | 8 | Sprint 3 | Data | Ready | BR-07; FR-015–016
EPIC-4 | Story | US-006 | Versioned risk rule administration | Should | 8 | Sprint 3 | Compliance | Ready | FR-017
EPIC-4 | Story | US-007 | Knowledge exclusion control | Should | 5 | Sprint 3 | Knowledge | Ready | FR-018
EPIC-5 | Task | AI-01 | Evaluation dataset and scoring harness | Must | 13 | Sprint 1 | Data | Done | BR-03–04
EPIC-5 | Task | OPS-01 | Pilot support and rollback runbook | Must | 5 | Sprint 3 | Support | Ready | FR-020; NFR-012
EPIC-6 | Story | US-009 | Additional language support | Could | 13 | Future | Product | Backlog | BR-09

## RTM
Requirements Traceability Matrix
Business requirement to implementation and test coverage.
Business Req | Functional Req | Stories | Test Cases | Test Status | Coverage | Owner | Notes
BR-01 | FR-013; FR-020 | US-004 | TC-008; TC-012 | UAT | Covered | Support Manager | Handling time and fallback
BR-02 | FR-002–004 | US-001 | TC-001; TC-002 | Passed | Covered | Product Manager | Classification
BR-03 | FR-005–008; FR-018 | US-002; US-007 | TC-003; TC-004; TC-010 | UAT | Covered | Knowledge Owner | Grounding and source lineage
BR-04 | FR-009–012; FR-017 | US-003; US-004; US-006 | TC-005; TC-006; TC-007 | UAT | Covered | Compliance | Mandatory review
BR-05 | FR-008; FR-014 | US-004; US-008 | TC-008; TC-009 | Passed | Covered | Compliance | Audit evidence
BR-06 | FR-001 | US-008 | TC-011; TC-013 | UAT | Covered | Security | Privacy and access
BR-07 | FR-015–016 | US-005 | TC-014; TC-015 | Ready | Covered | Data Analyst | KPI reconciliation
BR-08 | FR-012; FR-019 | US-004 | TC-007 | UAT | Covered | Support Manager | Feedback capture
BR-09 | Future | US-009 | Future | Backlog | Deferred | Product Manager | Outside pilot

## Data Mapping
Data Mapping
Field-level lineage for CRM, AI orchestration, knowledge, audit, and analytics.
Business Field | Source System | Source Field | Type | Target System | Target Field | Transformation | Validation | Classification | Retention
case_id | CRM Case | case_id | UUID | AI request | caseId | None | Required; immutable | Confidential | CRM policy
customer_message | CRM Case | latest_message | String | AI request | message | Normalize and redact before LLM | Required; max 20k chars | Restricted | CRM policy
channel | CRM Case | channel | Enum | AI request | channel | Map to EMAIL or WEB | Pilot values only | Internal | 13 months
customer_segment | CRM Account | segment | Enum | AI request | customerSegment | Approved lookup | Unknown maps to STANDARD | Confidential | CRM policy
category | AI response | category | Enum | CRM Case | ai_category | Taxonomy version required | Approved code | Internal | 13 months
class_confidence | AI response | confidence | Decimal | CRM Case | ai_confidence | Round to 4 decimals | 0 to 1 | Internal | 13 months
risk_flags | AI response | riskFlags | Array | CRM Case | ai_risk_flags | Approved codes | Multiple allowed | Restricted | 13 months
source_ids | Retrieval | sources | Array | Audit Event | source_ids | Store ID and version | At least one for draft | Internal | 13 months
draft_text | AI response | draft | String | CRM Case | ai_draft | Preserve original | No unsupported factual draft | Restricted | CRM policy
disposition | Agent action | action | Enum | Audit Event | disposition | Canonical codes | Required | Internal | 13 months
prompt_version | Orchestrator | promptVersion | String | Audit Event | prompt_version | None | Required for draft | Internal | 13 months
correlation_id | Gateway | correlationId | UUID | All services | correlation_id | Propagate unchanged | Required | Internal | 13 months

## API Requirements
API Requirements
Interface contract and error-handling expectations for the pilot.
ID | Method | Endpoint | Purpose | Authentication | Headers | Request | Success | Errors | Performance
API-001 | POST | /v1/support/analyze | Classify, risk score, retrieve, draft | OAuth2 service token | Idempotency-Key; X-Correlation-ID | JSON request | 200 analysis result | 400,401,403,409,422,429,503 | 8 sec p95
API-002 | POST | /v1/support/{caseId}/feedback | Record agent disposition | OAuth2 user token | X-Correlation-ID | Disposition, reason, corrections | 201 feedback ID | 400,401,403,404,409 | 3 sec p95
API-003 | POST | /v1/knowledge/search | Retrieve approved passages | Service token | X-Correlation-ID | Query and access context | 200 ranked sources | 400,401,403,429,503 | 3 sec p95
API-004 | GET | /v1/policy/rules | Read active routing rules | Compliance role | If-None-Match | None | 200 rules and version | 401,403,404 | 2 sec p95
API-005 | POST | /v1/metrics/events | Ingest audit and metric events | Service token | Idempotency-Key | Event batch | 202 accepted IDs | 400,401,409,413,429,503 | 5 sec p95

## UAT Cases
UAT Plan and Test Cases
Business acceptance evidence. Update Actual Result, Status, Evidence, and Defect ID during execution.
Test ID | Trace | Scenario | Precondition | Steps | Expected Result | Actual Result | Status | Evidence | Defect ID | Priority
TC-001 | US-001 | Valid billing request | Approved taxonomy loaded | Submit duplicate-charge request | Billing duplicate charge, confidence shown, normal priority |  | Not Run |  |  | High
TC-002 | FR-009 | Confidence threshold boundary | Threshold 0.80 | Test 0.79 and 0.80 scores | 0.79 routes to review; 0.80 follows risk and source rules |  | Not Run |  |  | High
TC-003 | US-002 | Approved source cited | Active KB-184 | Analyze supported billing request | Draft cites KB-184 version and opens source |  | Not Run |  |  | High
TC-004 | FR-007 | No approved source | No matching source | Analyze unsupported question | No factual draft; agent research instruction appears |  | Not Run |  |  | Critical
TC-005 | US-003 | High-risk topic override | Privacy risk rule active | Submit privacy deletion complaint with 0.95 confidence | Specialist routing and send blocked |  | Not Run |  |  | Critical
TC-006 | FR-010 | Threat and safety routing | Safety rule active | Submit threat content | Specialist routing before drafting |  | Not Run |  |  | Critical
TC-007 | US-004 | Reject requires reason | Draft available | Choose Reject without and with reason | Cannot submit without reason; event recorded with reason |  | Not Run |  |  | High
TC-008 | FR-014 | Complete audit trail | Approved draft | Approve and send response | Case, model, prompt, source, actor, disposition and timestamps linked |  | Not Run |  |  | Critical
TC-009 | US-008 | Idempotent retry | Known idempotency key | Repeat analyze request | Original result returned; no duplicate events |  | Not Run |  |  | High
TC-010 | US-007 | Excluded knowledge | Article initially active | Exclude article and search after 15 minutes | Article absent and change logged |  | Not Run |  |  | High
TC-011 | NFR-006 | Sensitive data redaction | Redaction configured | Submit message with test SSN and email | Prohibited identifier absent from model payload; event logged |  | Not Run |  |  | Critical
TC-012 | FR-020 | Provider failure fallback | Failure simulation enabled | Trigger provider timeout | Manual CRM workflow available and case preserved |  | Not Run |  |  | Critical
TC-013 | NFR-005 | Role access | Agent and compliance users | Open rule administration as each role | Agent denied; compliance user allowed; decisions logged |  | Not Run |  |  | High
TC-014 | US-005 | KPI filter and drill-through | Pilot events loaded | Filter by date and category | Metrics and records reflect filter population |  | Not Run |  |  | Medium
TC-015 | FR-016 | Dashboard reconciliation | Known event sample | Compare dashboard to SQL control totals | Counts and rates match within defined rounding |  | Not Run |  |  | High

## Defect Log
Defect Log
Illustrative defects identified during system testing. UAT defects should use the same schema.
Defect ID | Test ID | Summary | Severity | Status | Owner | Opened | Target | Area | Observed | Resolution | Retest | Closed
DEF-001 | TC-002 | Threshold rounds 0.795 to 0.80 before routing | 2 High | Open | Engineering | 2026-09-16 | 2026-09-20 | Routing | 0.795 displays as 0.80 and bypasses review | Compare using unrounded value; display separately
DEF-002 | TC-008 | Audit event omits knowledge version after agent edit | 1 Critical | In Progress | Engineering | 2026-09-16 | 2026-09-19 | Audit | Edited response retains source ID but loses version | Persist retrieval snapshot with disposition event
DEF-003 | TC-014 | Category filter excludes cases corrected by agent | 3 Medium | Ready to Retest | Data | 2026-09-17 | 2026-09-21 | Dashboard | Dashboard uses original AI category | Use final category with original available for analysis
DEF-004 | TC-011 | Redaction misses spaced test identifier | 2 High | Open | Security | 2026-09-17 | 2026-09-20 | Privacy | Pattern with spaces reaches model payload | Add normalization and test variants

## Evaluation Design
AI Evaluation and Outcome Study
Pre-specified measures, samples, thresholds, and interpretation rules for the pilot.
Dimension | Measure | Population | Threshold | Analysis Rule | Why It Matters | Owner
Intent classification | Macro F1 | Stratified labeled set | ≥ 0.88 | Report per-class recall | Balances common and rare classes | Data Lead
Critical intent | Recall | All critical labeled cases | ≥ 0.95 per class | No class hidden by average | Protects asymmetric-risk categories | Compliance
Risk detection | Recall and lower 95% bound | Adjudicated high-risk set | 100% observed | Report confidence bound | Quantifies uncertainty despite zero observed misses | Compliance
Confidence | Expected calibration error | Labeled validation set | ≤ 0.05 | Reliability curve required | Supports defensible threshold selection | ML Lead
Grounding | Supported-claim rate | Blind weekly draft sample | ≥ 98% | 95% confidence interval | Tests factual support, not fluency | Quality Lead
Retrieval | Recall at 5 | Answerable benchmark | ≥ 95% | Source must contain needed evidence | Separates retrieval from generation failure | Knowledge Owner
Operational effect | Handling minutes per resolved case | Eligible pilot and comparison cases | Improvement | Adjust for category and complexity | Measures labor effect | Support Manager
Customer outcome | CSAT and reopen rate | Survey and CRM records | No material deterioration | Report response and missingness | Protects outcome quality | Product
Fairness | Error and escalation difference | Approved customer segments | Investigate material gap | Minimum subgroup size applies | Detects hidden aggregate disparities | Compliance
Study design field | Specification
Unit of analysis | Customer case
Primary comparison | Eligible cases assigned AI assistance versus business-as-usual
Assignment | Randomized within category and shift when operationally feasible
Contamination control | All messages in one case remain in one group
Primary estimand | Difference in mean handling time for assigned groups
Quality constraint | No deterioration beyond approved margin for CSAT, reopen, or risk capture
Missing data | Report missingness by group; do not convert missing outcomes to zero
Protocol deviations | Record before analysis and include sensitivity analysis

## Business Case
Risk Adjusted Business Case
Editable scenario drivers. Results represent capacity value, not committed cash savings.
Driver | Downside | Base | Upside | Selected Base
Monthly requests | 10000 | 10000 | 10000 | 10000
Eligible share | 50% | 65% | 80% | 65%
Adoption among eligible | 45% | 70% | 85% | 70%
Minutes saved per assisted case | 1.5 | 3.5 | 5 | 3.5
Loaded labor cost per hour | 28 | 32 | 36 | 32
Variable AI cost per case | 0.45 | 0.3 | 0.2 | 0.3
Monthly fixed operating cost | 4500 | 3500 | 3000 | 3500
One-time implementation cost | 180000 | 140000 | 120000 | 140000
Base Case Result | Value |  | Scenario | Gross Hours | Gross Value | Net Monthly | Payback Months
Eligible requests | 6500 |  | Downside | 56.25 | 1575 | -3937.5 | No payback
Assisted requests | 4550 |  | Base | 265.4167 | 8493.3333 | 3628.3333 | 38.5852
Gross hours released | 265.4167 |  | Upside | 566.6667 | 20400 | 16040 | 7.4813
Gross monthly capacity value | 8493.3333
Monthly variable AI cost | 1365
Monthly net operating benefit | 3628.3333
Annual net operating benefit | 43540
Simple payback months | 38.5852

## Governance RAID
Governance RAID and Decision Log
Ownership, risks, assumptions, issues, dependencies, and formal decisions.
ID | Type | Description | Probability | Impact | Response | Owner | Status | Review
R-01 | Risk | Incomplete or stale knowledge | High | High | Inventory, owner assignment, freshness SLA | Knowledge Owner | Open | Weekly
R-02 | Risk | Automation bias among agents | Medium | High | Training, source verification, targeted sampling | Support Manager | Open | Weekly
R-03 | Risk | Historical labels encode inconsistent routing | High | Medium | Relabel stratified sample and adjudicate | Data Lead | In Progress | Design gate
R-04 | Risk | Review effort erodes capacity value | Medium | High | Measure review time and adjust eligibility | Product Manager | Open | Pilot
A-01 | Assumption | CRM supports required APIs and timestamps | Open | High | Interface spike and data profiling | Engineering Lead | Open | Discovery
I-01 | Issue | Support and Finance use different cost definitions | Open | Medium | Approve common semantic definition | Data Analyst | Open | Design gate
D-01 | Dependency | Security and privacy reviews precede UAT | Open | High | Schedule evidence review in design | Compliance Lead | Open | UAT entry
Decision ID | Decision | Accountable | Evidence Required | Date | Status
DEC-01 | Approve pilot scope | Product Manager | Charter, baseline, stakeholder findings |  | Pending
DEC-02 | Approve risk taxonomy | Compliance Lead | Policy, scenario tests, legal review |  | Pending
DEC-03 | Approve UAT entry | Engineering Lead | Build evidence, security results, open defects |  | Pending
DEC-04 | Approve controlled pilot | Support Manager | UAT exit report and operating runbook |  | Pending
DEC-05 | Approve expansion | Executive Sponsor | Four-week scorecard and residual-risk acceptance |  | Pending